## History & Schedule
Asphalt Paving Maintenance Record - Sample
Building Name or Number | 2018 | [6 empty] | 2019 | [6 empty] | 2020 | [6 empty] | 2021 | [6 empty] | 2022 | [6 empty] | 2023 | [6 empty] | 2024 | [6 empty] | 2025
| CS | ES | SC | MS | P | Str | $ | CS | ES | SC | MS | P | Str | $ | CS | ES | SC | MS | P | Str | $ | CS | ES | SC | MS | P | Str | $ | CS | ES | SC | MS | P | Str | $ | CS | ES | SC | MS | P | Str | $ | CS | ES | SC | MS | P | Str | $ | CS | ES | SC | MS | P | Str | $
1 | [7 empty] | X |  |  |  |  | X |  | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
2 | X |  |  |  |  | X | [8 empty] | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
4 |  |  | X | [9 empty] | X | [8 empty] | X |  |  |  |  | X |  | X |  |  |  |  | X |  | X |  | X |  |  | X
5 | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X | [15 empty] | X |  | X |  |  | X
6 | [9 empty] | X |  |  | X | [15 empty] | X |  |  |  |  | X
7 | [7 empty] | X |  |  |  |  | X |  | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
8 | [7 empty] | X |  |  |  |  | X |  | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
9 | [7 empty] | X |  |  |  |  | X |  | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
10 | [7 empty] | X |  |  |  |  | X |  | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
11 | [7 empty] | X |  | X |  |  | X | [15 empty] | X |  |  |  |  | X
12 | [7 empty] | X |  |  |  |  | X |  | X |  | X |  |  | X |  | X |  |  |  |  | X |  |  |  | X
13 |  |  | X |  |  | X |  | X |  | X |  |  | X | [8 empty] | X |  | X |  |  | X
14 | [7 empty] | X |  |  |  |  | X |  | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
15 | X |  | X |  |  | X | [22 empty] | X | [6 empty] | X |  | X |  |  | X
16 | [7 empty] | X |  | X |  |  | X | [6 empty] | X
17 | [7 empty] | X |  |  |  |  | X |  |  |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
18 | [7 empty] | X |  |  |  |  | X |  | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
19 | [7 empty] | X |  | X |  |  | X | [15 empty] | X |  |  |  |  | X |  | X |  | X |  |  | X
20 | [7 empty] | X |  | X |  |  | X |  | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
21 | [12 empty] | X | [8 empty] | X |  | X |  |  | X
22 | [14 empty] | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
23 | X |  |  |  |  | X | [8 empty] | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
25 | X |  |  |  |  | X | [8 empty] | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
26 | [7 empty] | X |  |  |  |  | X |  | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
29 | X |  | X |  |  | X | [15 empty] | X
31 | X |  |  |  |  | X | [22 empty] | X |  | X |  |  | X
39 | [7 empty] | X |  | X |  |  | X | [15 empty] | X |  |  |  |  | X
40 | [26 empty] | X
41 | [14 empty] | X |  | X |  |  | X | [8 empty] | X |  |  |  |  | X
42 | X |  | X |  |  | X | [22 empty] | X |  | X |  |  | X
Total Costs | 2018 | [5 empty] | 0 | 2011 | [5 empty] | 0 | 2020 | [5 empty] | 0 | 2021 | [5 empty] | 0 | 2022 | [5 empty] | 0 | 2023 | [5 empty] | 0 | 2024 | [5 empty] | 0 | 2025 | [5 empty] | 0
Estimated Longevity of Different Materials: | [7 empty] | Crack Fill - 1 to 2 years
Crack Seal - 3 to 8 years
Emulsion Seal - 3 to 5 years
Penetrating Seal - 4 to 7 years
Slurry Seal - 5 to 7 years
Note on B2: Year work is performed
Note on I2: Year work is performed
Note on P2: Year work is performed
Note on W2: Year work is performed
Note on AD2: Year work is performed
Note on AK2: Year work is performed
Note on AR2: Year work is performed
Note on AY2: Year work is performed
Note on B3: Crack Seal
Note on C3: Emulsion Seal
Note on D3: Slurry Seal
Note on E3: Miscellaneous Seal. Define with a cell comment.
Note on F3: Asphalt Patch
Note on G3: Paint Striping
Note on H3: Total amount spent on parking lot repairs
Note on I3: Crack Seal
Note on J3: Emulsion Seal
Note on K3: Slurry Seal
Note on L3: Miscellaneous Seal. Define with a cell comment.
Note on M3: Asphalt Patch
Note on N3: Paint Striping
Note on O3: Total amount spent on parking lot repairs
Note on P3: Crack Seal
Note on Q3: Emulsion Seal
Note on R3: Slurry Seal
Note on S3: Miscellaneous Seal. Define with a cell comment.
Note on T3: Asphalt Patch
Note on U3: Paint Striping
Note on V3: Total amount spent on parking lot repairs
Note on W3: Crack Seal
Note on X3: Emulsion Seal
Note on Y3: Slurry Seal
Note on Z3: Miscellaneous Seal. Define with a cell comment.
Note on AA3: Asphalt Patch
Note on AB3: Paint Striping
Note on AC3: Total amount spent on parking lot repairs
Note on AD3: Crack Seal
Note on AE3: Emulsion Seal
Note on AF3: Slurry Seal
Note on AG3: Miscellaneous Seal. Define with a cell comment.
Note on AH3: Asphalt Patch
Note on AI3: Paint Striping
Note on AJ3: Total amount spent on parking lot repairs
Note on AK3: Crack Seal
Note on AL3: Emulsion Seal
Note on AM3: Slurry Seal
Note on AN3: Miscellaneous Seal. Define with a cell comment.
Note on AO3: Asphalt Patch
Note on AP3: Paint Striping
Note on AQ3: Total amount spent on parking lot repairs
Note on AR3: Crack Seal
Note on AS3: Emulsion Seal
Note on AT3: Slurry Seal
Note on AU3: Miscellaneous Seal. Define with a cell comment.
Note on AV3: Asphalt Patch
Note on AW3: Paint Striping
Note on AX3: Total amount spent on parking lot repairs
Note on AY3: Crack Seal
Note on AZ3: Emulsion Seal
Note on BA3: Slurry Seal
Note on BB3: Miscellaneous Seal. Define with a cell comment.
Note on BC3: Asphalt Patch
Note on BD3: Paint Striping
Note on BE3: Total amount spent on parking lot repairs
Note on H4: Insert the dollar amount of the work and any desired miscellaneous information such as the contractor and how well they did.
Note on O4: Insert the dollar amount of the work and any desired miscellaneous information such as the contractor and how well they did.
Note on V4: Insert the dollar amount of the work and any desired miscellaneous information such as the contractor and how well they did.
Note on AC4: Insert the dollar amount of the work and any desired miscellaneous information such as the contractor and how well they did.
Note on AJ4: Insert the dollar amount of the work and any desired miscellaneous information such as the contractor and how well they did.
Note on AQ4: Insert the dollar amount of the work and any desired miscellaneous information such as the contractor and how well they did.
Note on AX4: Insert the dollar amount of the work and any desired miscellaneous information such as the contractor and how well they did.
Note on BE4: Insert the dollar amount of the work and any desired miscellaneous information such as the contractor and how well they did.

## Maintenance Detail
BLDG | Date | PO | Contractor | Work Performed | Price
1 | 2009-10-01 | FGC2224452P | Morgan Pavement Maintenance | Fill cracks with hot rubber crack sealant. Includes waterways. | 2,350.00 USD
1 | 2011-02-02 | FGC2224851P | M and M Asphalt Services Inc | Apply rubberized asphalt crack seal to all cracks 1/8" and larger, Re-stripe parking lot as is | 2,670.00 USD
1 | 2012-03-12 | FGC2225217P | M and M Asphalt Services Inc | Apply 1 coat primer, 2 coats seal coat to parking lot, Apply crack sealer to 5530 linear feet, Striping | 8,433.68 USD
2 | 2009-11-13 | FGC2224485P | Morgan Pavement Maintenance | Asphalt: Line-cut perimeter and remove broken asphalt and debris; tackcoat edges; apply and finish 3 inches of new hot-mix asphalt | 7,880.00 USD
2 | 2010-04-20 | FGC2224632P | Morgan Pavement Maintenance | Crack repair and striping, per proposal dated March 24, 2010 (Aaron Edwards) | 2,650.00 USD
2 | 2012-03-12 | FGC2225219P | Morgan Pavement Maintenance | Crack repair, Asphalt slurry seal, Asphalt patching, Striping | 12,115.00 USD
2 | 2012-04-25 | FGC2225278P | Morgan Pavement Maintenance | Asphalt patching (trench patching), Asphalt patching (5x5 patch) | 3,005.75 USD
4 | 2010-04-14 | FGC2224617P | Morgan Pavement Maintenance | Crack repair, asphalt Type 1 slurry seal, striping | 12,065.00 USD
4 | 2010-04-19 | FGC2224625P | Morgan Pavement Maintenance | Line cut perimeter and remove broken asphalt and debris; check for proper road base; tackcoat edges; apply and finish 3 inches of new hot-mix asphalt | 4,310.00 USD
4 | 2011-11-14 | FGC2225098P | M and M Asphalt Services Inc | Paint two handicap symbols in parking stalls. Approx: | 500.00 USD
5 | 2009-10-01 | FGC2224453P | Morgan Pavement Maintenance | Fill cracks with hot rubber crack sealant. This is for all of the edges where the concrete meets the asphalt. | 1,625.00 USD
5 | 2010-04-20 | FGC2224627P | Morgan Pavement Maintenance | Asphalt slurry seal and striping, per bid dated Mar 24 2010 (Aaron Edwards) | 13,655.00 USD
5 | 2010-09-27 | FGC2224759P | Morgan Pavement Maintenance | Striping in parking lot | 350.00 USD
5 | 2010-09-28 | FGC2224760P | Morgan Pavement Maintenance | Parking lot striping work | 350.00 USD
5 | 2010-09-30 | FGC2224763P | Morgan Pavement Maintenance | Asphalt patching | 1,740.00 USD
5 | 2012-09-10 | FGC2225510P | Morgan Pavement Maintenance | Crack seal and re-stripe parking lot. | 5,461.00 USD
6 | 2009-10-01 | FGC2224454P | Morgan Pavement Maintenance | Fill cracks with hot rubber crack sealant | 1,940.00 USD
6 | 2011-02-02 | FGC2224852P | Morgan Pavement Maintenance | Asphalt slurry seal, Re-stripe parking lot per current layout | 6,130.00 USD
7 | 2008-03-26 | FGC2224110C | Morgan Pavement Maintenance | Parking Lot Emulsion Sealer | 11,860.00 USD
7 | 2011-02-02 | FGC2224848P | M and M Asphalt Services Inc | Apply rubberized asphalt crack seal to all cracks 1/8" and larger, Re-stripe parking lot as is | 2,598.00 USD
7 | 2012-03-12 | FGC2225233P | M and M Asphalt Services Inc | 1 coat primer, 2 coats seal coat, Crack sealer, Striping | 10,806.54 USD
8 | 2011-02-02 | FGC2224853P | Morgan Pavement Maintenance | Crack repair, Re-stripe lot per current layout | 4,795.00 USD
8 | 2012-03-12 | FGC2225220P | Morgan Pavement Maintenance | Crack repair, Asphalt slurry seal, Striping | 14,857.00 USD
9 | 2008-03-26 | FGC2224111C | Morgan Pavement Maintenance | Parking Lot Emulsion Sealer | 11,520.00 USD
9 | 2011-02-02 | FGC2224854P | Morgan Pavement Maintenance | Crack repair, including GAP for large cracks, Re-stripe parking lot per current layout | 4,995.00 USD
9 | 2012-03-12 | FGC2225221P | Morgan Pavement Maintenance | Crack repair, Asphalt slurry seal, Striping | 12,875.00 USD
10 | 2011-02-02 | FGC2224855P | Morgan Pavement Maintenance | Crack repair, Repair edges where concrete meets asphalt, Re-stripe parking lot per current layout | 3,630.00 USD
10 | 2012-03-12 | FGC2225222P | Morgan Pavement Maintenance | Crack repair, Asphalt slurry seal, Striping | 10,687.00 USD
11 | 2008-07-02 | FGC2224231P | Morgan Pavement Maintenance | Stripe all lines and paint handicap approved spaces | 340.00 USD
11 | 2011-02-03 | FGC2224869P | Morgan Pavement Maintenance | Crack repair, asphalt slurry seal and striping per proposal dated 02-01-11 (Aaron Edwards) | 16,730.00 USD
11 | 2012-06-01 | FGC2225306P | Morgan Pavement Maintenance | Asphalt patching, per bid by Brad Searle | 1,200.00 USD
12 | 2008-03-21 | FGC2224105P | Morgan Pavement Maintenance | Asphalt patching, per bid | 2,930.00 USD
12 | 2008-03-26 | FGC2224114C | Morgan Pavement Maintenance | Parking Lot Slurry Seal | 8,590.00 USD
12 | 2011-02-02 | FGC2224856P | Morgan Pavement Maintenance | Crack repair, Re-stripe lot per current layout | 4,240.00 USD
12 | 2012-03-12 | FGC2225223P | Morgan Pavement Maintenance | Crack repair, Asphalt slurry seal, Striping | 11,045.00 USD
12 | 2012-09-14 | FGC2225526P | Morgan Pavement Maintenance | Asphalt patching: Line cut perimeter and remove broken asphalt; replace 6 inches of road base; tack-coat edges; apply and finish 3 inches of new hot-mix asphalt. | 3,087.00 USD
12 | 2012-10-11 | FGC2225568P | Morgan Pavement Maintenance | Asphalt removal & patching (2250 sq ft), Asphalt patching (900 sq ft) | 12,041.00 USD
12 | 2012-10-16 | FGC2225571P | Morgan Pavement Maintenance | Paint "In" and "Out" arrows on parking lot ingress and egress areas. | 250.00 USD
13 | 2010-04-16 | FGC2224622P | M and M Asphalt Services Inc | Apply slurry Type I to parking lot, Striping | 7,268.88 USD
13 | 2011-11-03 | FGC2225097P | M and M Asphalt Services Inc | Paint 4 parking stalls with handicap symbol | 1,000.00 USD
13 |  | FGC2224967P | Morgan Pavement Maintenance | Evaluation of parking lot water pooling problem | 0.00 USD
14 | 2011-02-02 | FGC2224857P | Morgan Pavement Maintenance | Crack repair, Re-stripe lot per current layout | 3,945.00 USD
14 | 2012-03-12 | FGC2225224P | Morgan Pavement Maintenance | Crack repair, Custom asphalt sealcoat, Striping | 16,290.00 USD
14 | 2012-07-03 | FGC2225348P | Morgan Pavement Maintenance | Asphalt patching, minimum of 148 sq ft, | 1,200.00 USD
15 | 2008-03-21 | FGC2224100P | Morgan Pavement Maintenance | Parking lot crack repair, Re-striping of parking lot | 3,045.00 USD
15 | 2010-04-20 | FGC2224626P | Morgan Pavement Maintenance | Asphalt patching, crack repair, slurry seal, striping, concrete. Refer to bid dated Mar 24, 2010 (Aaron Edwards) | 32,691.00 USD
16 | 2011-02-07 | FGC2224871P | M and M Asphalt Services Inc | Crack seal, 1 coat primer, 2 coats seal coat and re-striping per bid by Chris Hanks (01-31-11) | 17,636.63 USD
16 | 2011-06-06 | FGC2224980P | M and M Asphalt Services Inc | Dig out 180 sq ft of asphalt and replace with 3 inches of asphalt | 900.00 USD
16 | 2012-02-28 | FGC2225194P | Morgan Pavement Maintenance | 12' x 40' x 6" concrete dumpster pad: Sawcut and tear out existing asphalt and replace with concrete. | 5,300.00 USD
16 | 2012-05-23 | FGC2225298P | M and M Asphalt Services Inc | Parking lot striping. | 450.00 USD
17 | 2009-10-01 | FGC2224450P | Morgan Pavement Maintenance | Install asphalt ramp at north storage shed entrance | 1,150.00 USD
17 | 2011-02-08 | FGC2224875P | M and M Asphalt Services Inc | Apply rubberized asphalt crack seal to all cracks 1/8" and larger, Re-stripe parking lot as is | 850.00 USD
17 | 2012-03-12 | FGC2225218P | M and M Asphalt Services Inc | Apply 1 coat primer, 2 coats seal coat to parking lot, Striping | 1,053.13 USD
18 | 2008-03-26 | FGC2224112C | Morgan Pavement Maintenance | Parking Lot Slurry Seal | 12,065.00 USD
18 | 2011-02-02 | FGC2224849P | M and M Asphalt Services Inc | Apply rubberized asphalt crack seal to all cracks 1/8" and larger, Re-stripe parking lot as is | 3,354.00 USD
18 | 2012-03-12 | FGC2225225P | Morgan Pavement Maintenance | Crack repair, Asphalt patching, Asphalt slurry seal, Striping, Remove second ramp | 15,059.00 USD
18 |  | FGC2225005P | M and M Asphalt Services Inc | Paint sections of curb red, per Ray Bradley | 0.00 USD
19 | 2011-02-03 | FGC2224870P | Morgan Pavement Maintenance | Crack repair, asphalt slurry seal and striping per proposal dated 02-01-11 (Aaron Edwards) | 18,888.00 USD
19 | 2012-11-13 | FGC2225617P | Morgan Pavement Maintenance | Patch areas of parking lot as designated. | 1,200.00 USD
20 | 2008-03-26 | FGC2224113C | Morgan Pavement Maintenance | Parking Lot Emulsion Sealer | 13,405.00 USD
20 | 2009-05-06 | FGC2224380P | Morgan Pavement Maintenance | Parking lot area by southwest entrance: Patch asphalt per quote dated May 4, 2009 (Aaron Edwards) | 900.00 USD
20 | 2011-02-03 | FGC2224868P | Morgan Pavement Maintenance | Crack repair, asphalt patching and striping per proposal dated 02-01-2011 (Aaron Edwards) | 11,760.00 USD
20 | 2012-03-12 | FGC2225226P | Morgan Pavement Maintenance | Crack repair, Custom asphalt sealcoat, Striping | 15,160.00 USD
21 | 2009-10-01 | FGC2224451P | Morgan Pavement Maintenance | Fill cracks with hot rubber crack sealant. Includes waterways and edges where concrete meets asphalt. | 600.00 USD
21 | 2011-10-19 | FGC2225089P | M and M Asphalt Services Inc | Stencil "Visitor Parking Only" on curb of street parking. | 800.00 USD
22 | 2012-03-12 | FGC2225227P | Morgan Pavement Maintenance | Crack repair, Asphalt slurry seal, Striping | 13,195.00 USD
22 | 2012-07-30 | FGC2225374P | Morgan Pavement Maintenance | Asphalt patching (285 sq ft minimum), Striping, with 8 handicap spaces | 1,450.00 USD
23 | 2008-03-21 | FGC2224101P | Morgan Pavement Maintenance | Parking lot crack repair | 2,730.00 USD
23 | 2010-04-20 | FGC2224633P | M and M Asphalt Services Inc | Crack seal and striping, per proposal dated Jan 29, 2010 (Chris Hanks) | 2,550.00 USD
23 | 2012-03-12 | FGC2225234P | M and M Asphalt Services Inc | 1 coat primer, 2 coats seal coat, Crack sealer, Striping | 10,448.00 USD
25 | 2008-03-21 | FGC2224102P | Morgan Pavement Maintenance | Parking lot crack repair | 2,550.00 USD
25 | 2010-04-20 | FGC2224631P | Morgan Pavement Maintenance | Crack repair and striping, per bid dated March 24, 2010 (Aaron Edwards) | 2,010.00 USD
25 | 2012-03-12 | FGC2225228P | Morgan Pavement Maintenance | Crack repair, Asphalt slurry seal, Striping, Gap material | 14,201.00 USD
25 | 2012-05-10 | FGC2225287P | Morgan Pavement Maintenance | Asphalt patching. | 4,000.00 USD
25 | 2012-06-01 | FGC2225307P | Morgan Pavement Maintenance | Asphalt patching, per bid by Brad Searle | 1,426.00 USD
26 | 2008-03-26 | FGC2224115C | M and M Asphalt Services Inc | Parking Lot Emulsion Sealer | 11,260.00 USD
26 | 2011-02-02 | FGC2224850P | M and M Asphalt Services Inc | Apply rubberized asphalt crack seal to all cracks 1/8" and larger, Re-stripe parking lot as is | 2,950.00 USD
26 | 2012-03-12 | FGC2225235P | M and M Asphalt Services Inc | 1 coat primer, 2 coats seal coat, Crack sealer, Striping | 10,874.17 USD
29 | 2008-03-21 | FGC2224103P | Morgan Pavement Maintenance | Parking lot crack repair | 1,975.00 USD
29 | 2010-04-16 | FGC2224623P | M and M Asphalt Services Inc | Parking lot crack seal, Seal coat, Striping | 9,667.88 USD
31 | 2009-10-01 | FGC2224455P | Morgan Pavement Maintenance | Fill cracks with hot rubber crack sealant. Includes waterways and edges where the concrete meets the asphalt. | 2,925.00 USD
31 | 2010-04-20 | FGC2224630P | Morgan Pavement Maintenance | Crack repair and striping, per bid dated March 24, 2010 (Aaron Edwards) | 7,685.00 USD
39 | 2011-03-29 | FGC2224919P | Morgan Pavement Maintenance | Crack repair, asphalt slurry seal and striping per proposal received 3-28-11 (Aaron Edwards) | 1,800.00 USD
40 | 2008-12-03 | FGC2224332P | Morgan Pavement Maintenance | Stripe concrete parking lot per current layout. | 1,295.00 USD
41 | 2012-03-12 | FGC2225229P | Morgan Pavement Maintenance | Crack repair, Asphalt patching, Asphalt slurry seal, Striping | 10,790.00 USD
42 | 2008-03-21 | FGC2224104P | Morgan Pavement Maintenance | Parking lot crack seal | 2,850.00 USD
42 | 2010-04-20 | FGC2224628P | M and M Asphalt Services Inc | Crack seal, Slurry Type I, Restripe parking lot | 10,611.20 USD